## Gantt Chart
GANTT CHART | [6 empty] | Project Deliverables ➜ | [7 empty] | Develop a web-based voterCRM application
PROJECT TITLE |  | Online VoterCRM |  |  |  |  | Institutaion Name | [8 empty] | IIIT Hyderabad & Great Learning
PROJECT MANAGER |  | Narayana Darapaneni |  |  |  |  | DATE | [8 empty] | 2023-09-24
Front End Team Lead
Back End Team Lead
Deployment Team Lead
Integration Team Lead
Analytics Team Lead
Database Team Lead
Testing Team Lead
Documentation Team Lead
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
[7 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
1 | Week -1 |  | 2023-09-24 | 2023-09-30 | 6
1.1 | Project Management | Nidadavolu Niranjan
1.1.1 | Project Architecture |  |  |  | 0 | 0%
1.1.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.1.3 | Project Documentation | Ajith Vijayan, Asijit Baruah, Spoorthy Reddy |  |  | 0 | 0%
1.1.4 | Minutes of Meetings - Documentation |  |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.2 | Frontend |  | 2023-09-24 | 2023-09-30 | 6
1.2.1. | Front End Architecture | Sarita Mahanty |  |  | 0 | 0%
1.2.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.2.3 | Front End Fields Finalizaiton | DEEKSHITULA S S V K BHARADWAJ, Khyati Dewan |  |  | 0 | 0%
1.2.4 | Login Page | Harshwardhan Rajkumar Padile, Ayush Saxena |  |  | 0 | 0%
1.2.5 | Subscription Plan Page | Shekar Kaki, Amol More |  |  | 0 | 0%
1.2.6 | Group Subscription | Supriyo Sinha, Prashanthi |  |  | 0 | 0%
1.2.7 | Sync with Google Drive, Dropbox, GitHub |  |  |  | 0 | 0%
1.2.8 | Usage Analytics |  |  |  | 0 | 0%
1.2.9 | Payment Module |  |  |  | 0 | 0%
1.2.10 | History |  |  |  | 0 | 0%
1.2.11 | Share with others |  |  |  | 0 | 0%
1.2.12 | Front End Documentation |  |  |  | 0 | 0%
1.2.13 | Analyse existing electionCare from frontend features & technolgies point of view |  |  |  | 0 | 0%
1.2.14 | Expected features from AWS and cost |  |  |  | 0 | 0%
1.2.15 | Minutes of Meetings - Documentation |  |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.3 | Backend |  | 2023-09-24 | 2023-09-30 | 6
1.3.0 | Data Collection of Vijayawada Central assembly constituency | Entire Team
| Extract voter data from pdf files and save it into an excel file as rows | Sarita Mahanty
1.3.1. | Back End Architecture | sree lakshmi Kudumula, Ramgopal Nayak Jarupla |  |  | 0 | 0%
1.3.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.3.3. | Database fields finalization | Syed Asrar Ahmed Hussain, Dharmagadi Vivek |  |  | 0 | 0%
1.3.4. | Database design | balu.86, M Naseemunisa |  |  | 0 | 0%
1.3.5 | Backend Documentation | Kaushik Pradhan, Mohammed Abdul Baseer Siddiqui |  |  | 0 | 0%
1.3.6 | Usage Analytics | Mrudula Jonnavithula |  |  | 0 | 0%
1.3.7 | Admin/User Table design (including different usage logs, payments, permissions, shares, submission, uploads, downloads, deletes etc) | Bhanuja G, Sarita Mahanty |  |  | 0 | 0%
1.3.8 | Analyse existing electionCare from backend features & technolgies point of view | Arunabh Pathak, Lakshmi Kondapuram |  |  | 0 | 0%
1.3.9 | Payment module backend logic |  |  |  | 0 | 0%
1.3.10 | Sync with Google Drive, Dropbox, GitHub |  |  |  | 0 | 0%
1.3.11 | History |  |  |  | 0 | 0%
1.3.12 | Share with others |  |  |  | 0 | 0%
1.3.13 | Analyse existing electionCare from backend features & technolgies point of view |  |  |  | 0 | 0%
1.3.14 | Expected features from AWS and cost |  |  |  | 0 | 0%
1.3.15 | Minutes of Meetings - Documentation |  |  |  | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
[5 empty] | 0 | 0%
1.4 | Deployment |  | 2023-09-24 | 2023-09-30 | 6
1.4.1. | Deployment Architecture | Omkar Jawaji |  |  | 0 | 0%
1.4.2 | Week2 tasks recommendation | Maya Mahesh Narayana |  |  | 0 | 0%
1.4.3 | Deployment Plan | Anil Beerakayala |  |  | 0 | 0%
14.4 | Github account activation | Kavitha, Mudireddy Akhila |  |  | 0 | 0%
1.4.5 | AWS account features identification and account activation. AWS account will be provided by Great Learning. Reach out to Vaishnavi once required account features identified |  |  |  | 0 | 0%
1.4.6 | Analyse existing electionCare from deployment features & technolgies point of view | Mrudula Jonnavithula, Sweta |  |  | 0 | 0%
1.4.7 | Expected features from AWS and cost | Dhananjaya G, HARSHIT MEHTA |  |  | 0 | 0%
1.4.8 | Deploy locally (in your laptop or desktop) MVP | Ram Reddy T, Vaibhav Sharma |  |  | 0 | 0%
1.4.9 | Deploy in the free AWS account, the MVP | Madhuri, Rohit Garg |  |  | 0 | 0%
1.4.10 | Deployment Documentation |  |  |  | 0 | 0%
1.4.15 | Minutes of Meetings - Documentation |  |  |  | 0 | 0%
1.4 | Integration |  | 2023-09-24 | 2023-09-30 | 6
1.4.1. | Deployment Architecture |  |  |  | 0 | 0%
1.4.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.4.3 | Integration tech stack recommendation | D. Narayana
1.4 | Analytics |  | 2023-09-24 | 2023-09-30 | 6
1.4.1. | Deployment Architecture | Kavitha |  |  | 0 | 0%
1.4.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.4.3 | 30 required fields | D. Narayana
1.7 | Database |  | 2023-09-24 | 2023-09-30 | 6
1.7.1. | Database Architecture/Modelling |  |  |  | 0 | 0%
1.7.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
1.7.3 | defining purpose of Database
1.7.4 | Listing down major functional and non-functional requirements
1.7.5 | Choosing the Database(or combination of Databases) to be used
1.7.6 | Listing Down all entities to identify tables
1.7.7 | Deciding relationships between the tables
1.7.8 | Deciding the columns, keys and constraints
1.7.9 | Creating the ER Diagram
1.7.10 | Creating Schema(database, tables) using the ER Diagram
1.7.11 | Adding/Updating the Data into relevant tables
1.7.12 | Data Versioning and History
1.7.13 | 30 required fields | D. Narayana
1.4 | Testing |  | 2023-09-24 | 2023-09-30 | 6
1.4.1. | Deployment Architecture | SAURAV VISHWAKARMA, Jagadish A
1.4.2 | Frontend | Vamsi Krishna Alla, Arshad Ali Mohammed
1.4.3 | Backend | Shrabani pradhan, PATEL SAGAR BLAVANTBHAI |  |  | 0 | 0%
1.4.4 | Database | Madhuri |  |  | 0 | 0%
1.4 | Tech Architecture |  | 2023-09-24 | 2023-09-30 | 6
1.4.1. | Tech Architecture and stack research | Ram Reddy T, Vaibhav Sharma, Rohit Garg |  |  | 0 | 0%
1.4.2 | Tech Stack validation |  |  |  | 0 | 0%
1.5 | Documentation |  | 2023-09-24 | 2023-09-30 | 6
1.5.1. | Deployment Architecture |  |  |  | 0 | 0%
1.5.2 | Week2 tasks recommendation |  |  |  | 0 | 0%
0%
100%